## Sprint Backlog
Sprint (a week) | Task Name | Estimate time( hour) | Taken by | Actual Time | Status | Date Doing | Problems
1 | Requirement analyze | 24 | All members | 28 | Done | 2020-05-25 | Conflict ideas
2 | Design ERD | 16 | Phương Quang | 20 | Done | 2020-06-01
| Design Use case Diagram | 16 | Đức Thắng | 24 | Done | 2020-06-01 | Misunderstanding relationship
| Design Class Diagram | 16 | Đức Thắng | 16 | Done | 2020-06-04
3 | Use case Description (User) | 12 | Quang Minh | 12 | Done | 2020-06-08
| Use case Description (Admin) | 12 | Đức Thắng | 16 | Done | 2020-06-08 | Add missing function
| Design Database | 8 | Phương Quang | 8 | Done | 2020-06-08
4 | Overview | 20 | All members | 20 | Done | 2020-06-15
| Synchronize report | 4 | Quang Minh | 4 | Done | 2020-06-19
5 | Technical Research | 24 | All members | 28 | Done | 2020-06-22 | Looking for more technical
6 | Login/Logout | 5 | Phương Quang | 6 | Done | 2020-06-29
| Register | 10 | Phương Quang | 20 | Done | 2020-07-01
| Register Car | 10 | Đức Thắng | 14 | Done | 2020-06-29
| View(Car) | 10 | Đức Thắng | 12 | Done | 2020-07-01
| Manage Car | 10 | Quang Minh | 14 | Done | 2020-06-29
7 | Contact | 1 | Phương Quang | 1 | Done | 2020-07-06
| Edit Profile | 15 | Phương Quang | 15 | Done | 2020-07-09
| Manage Technology | 15 | Quang Minh | 16 | Done | 2020-06-07
| Get Product Info | 20 | Đức Thắng | 24 | Done | 2020-06-07
8 | Merge code | 14 | All members | 28 | Done | 13/07 | Conflict code
9 | Merge code | 5 | All members | 5 | Done | 20/07 | Conflict data
| Prepare Presentation | 10 | All members | 15 | Done | 23/07
10 | Maintain Software | 24 | All members | 28 | Done | 26/07 | Find bugs
| Prepare Presentation | 5 | All members | 5 | Done | 28/07